## Sheet1
| Date | 2023-11-15 | 2023-11-16
| Day | Wednesday | Thursday
| expected | 21 | 0
| actual | 13 | 8
For this sprint we expected to finish all of the tasks in the first day as we underestimated the time it would take to complete them. The lab time proved insufficient for us. The tasks that were leftover were then completed the following day outside of lab time.We may need to a) be more prepared coming into the labs and/or b) delegate some of the tasks to another day predicting that they may take more time than the two hours alloted to the lab.